## User Stories
This chart is dedicated to the sprint planning
Sprint 2
Issue # | User Story Title/Task Title | Description/Associated Tasks | Difficulty Level (0,1,2,3,5,8) | Priority | Risk | Assign | Sprint
#2 | As a system administrator, I want to create a new user | - Create UI for viewing and managing clients #44 - BackEnd Functionality to create new users #52 | 3- This is an imperative part of the functional requirement we need to ensure functionality and consistency | High | Low Risk- this is a low risk High value functional requirement | Benjamin Ho, Ikram Kamal | Sprint 2
#11 | As a system administrator, I want to create a new vehicle posting so that I can provide other users vehicles to rent | -Design functional MongoDB database schema for Vehicle information #58 - Create UI for viewing and modelling process #35 -Implement a validation logic for vehicle details #41 - Test the creation functionality to ensure proper creation #59 | 3- This is imperative since it is necessary for the product we are renting on our platform, and alot of details are involved for a vehicle so we need adequate time to work on this, we would also need to integrate both front endand backend for this task. | High | Low Risk- This is a low risk High value functional requirement | Uyi Oronsaye, Ikram Kamal | Sprint 2
#28 | As a system administrator, I want to be able to create new reservations in the system for customers | -Design and implement frontend reservation creation form #29 -Implement validation logic for form fields -Develop backend API endpoint for creating reservations -Update frontend to display confirmation message upon successful reservation creation | 3- This is imperative since it is necessary feature for our users. ease of use. | High | Low Risk- This is a low risk High value functional requirement | Samuel Henderson, Ikram Kamal | Sprint 2
#18 | As a client, I want to be able to access the vehicle catalog from homepage | -Create a "Catalog" link on the navigation bar #73 | 1- Provides good UX, and increases intuitiveness, and ease of access. | Low | Low Risk- This is a low risk High value functional requirement | Ikram Kamal | Sprint 2
#19 | As a client, I want to view the vehicle catalog | -Design UI for catalog | 3- Implement a good UI. Necessary feature to visualize the available vehicles | High | Low Risk- This is a low risk, Low value Not explicitly mentioned in our FRs | Hanine Tydrini | Sprint 2
#80 | As a client, I want to be able to select a vehicle on the catalog | -Redirect user to a new page when vehicle is selected #81 -Design UI for Vehicle pages #82 | 3- Implement a good UI. Necessary feature to visualize the available vehicles | High | Low Risk- Low Risk, low value | Hanine Tydrini | Sprint 2
#12 | As a customer, I want to be able to view my reservation so that I can edit user account details | - Design UI for a "My Reservations page" page #84 - Fetch data from database to display in UI #85 - Test functionality of search up | 3- Being able to dynamically edit reservation details is imperative | Medium | High RIsk | Hanine Tydrini, Yasmine Mouatif | Sprint 2
#78 | As a system administrator, I want to delete users, so that I can remove them from the system | -Design Ui for removing/modifying a user #103 -Backend functionality to delete a user #79 | 2 - This is imperative since it is a necessary feature to manage users. Research needed to properly implement API endpoint. | Medium | High RIsk | Benjamin Ho, Ikram Kamal | Sprint 2
#77 | As a system administrator, I want to Update information in the system so that I edit user accounts details | -Design UI for removing / modifying a user #103 - Backend functionality to update users #83 | 3 - This is imperative since it is a necessary feature to manage users. Research needed to properly implement API endpoint. | High | Low Risk- this is a low risk High value functional requirement | Benjamin Ho, Ikram Kamal | Sprint 2
#69 | As a customer, I want to delete my reservation so that I can cancel my plans | -Design UI for Delete Reservation Confirmation Popup #89 -Delete reservation from database #90 | 3- It's imperative to the overall flexibility of our plateform in accomodating users. | High | Low Risk- this is a low risk High value functional requirement | Yasmine Mouatif | Sprint 2
#57 | As a system Administrator, I shall be able to delete a specific vehicle from our system so that unavailable postings are not displayed | -Create UI search features to find vehicles via Unique ID #60 -Create a UI for viewing, and modelling process #35 - BackEnd functionality to delete a specific vehicle #66 -Implement verification process to give SA cancel a deletion #67 | 3- This is imperative for the success of our application as it is one of the core features. we would also need to integrate both front end and backend for this task. | High | Low Risk- this is a low risk High value functional requirement | Uyi Oronsaye, Ikram Kamal | Sprint 2
#56 | As a system Administrator, I shall be able to update details on a specific vehicle so that the details on vehicles are accurate | -BackEnd Functionality to update vehicle details #63 -Create a UI for viewing, and modelling process #35 -Implement validation logic for updated vehicle details #64 | 3- This is imperative for the success of our application as it is one of the core features. we would also need to integrate both front end and backend for this task. | High | Low Risk- this is a low risk High value functional requirement | Uyi Oronsaye, Ikram Kamal | Sprint 2
#55 | As a system Administrator, I shall have view privileges on details on a specific vehicle so that i can verify our postings | -Create UI search features to find vehicles via Unique ID #60 -Backend functionality to retrieve vehicle data associated with the unique ID #61 - Create a UI for viewing, and modelling process #35 | 2- This is imperative for the success of our application as it is one of the core features. | High | Low Risk- this is a low risk High value functional requirement | Uyi Oronsaye, Ikram Kamal | Sprint 2
#53 | As a customer, I want to modify my reservation so that I can change it's details | -Design UI for editable mode #87 -Update data in database upon modifications #88 | 3- It's imperative to the overall flexibility of our plateform in accomodating users. | High | Low Risk- this is a low risk High value functional requirement | Hanine Tydrini | Sprint 2
#51 | As a system administrator, I want to READ user's information in the system so that I can verify user accounts | -Design UI for viewing users #44 -Backend functionality to read the details of users #54 | 3- This is imperative since it is a necessary feature to manage users. Research needed to properly implement API endpoint. | High | Low Risk- this is a low risk High value functional requirement | Benjamin Ho, Ikram Kamal | Sprint 2
#32 | As a system administrator, I want to be able to cancel existing reservations in the system. | -Implement frontend option to cancel reservations. - Develop backend API endpoint for canceling reservations. -Update reservation status in the backend upon cancellation. -Ensure canceled reservations are excluded from active reservations list. | 3 - This is imperative since it is a necessary feature for our users. ease of use. Research needed to properly develop backend API endpoint | High | Low Risk- this is a low risk High value functional requirement | Samuel Henderson, Ikram Kamal | Sprint 2
#31 | As a system administrator, I want to be able to modify existing reservations in the system. | -Implement frontend option to edit reservations. -Develop backend API endpoint for updating reservations. -Design and implement reservation modification form. -Handle form submission and update reservation data in the backend. | 3 - This is imperative since it is a necessary feature for our users. ease of use. Research needed to properly develop backend API endpoint | High | Low Risk- this is a low risk High value functional requirement | Samuel Henderson, Ikram Kamal | Sprint 2
#30 | As a system administrator, I want to be able to view all existing reservations in the system. | -Design and implement frontend reservations list page. -Develop backend API endpoint for fetching reservations. -Implement filtering and search functionality in frontend. -Add scrolling feature to handle large lists of reservations. | 3 - This is imperative since it is a necessary feature for our users. ease of use. Research needed to properly develop backend API endpoint | High | Low Risk- this is a low risk High value functional requirement | Samuel Henderson, Ikram Kamal | Sprint 2
#27 | As a customer, I want to see a reservation summary and confirmation of my booking | -Set up the UI to display a reservation confirmation for the user after he has selected all options and details. #97 -Give the user options once he has selected confirm my booking #98 | 3- Creating and modifying reservations is the most difficult part. Once the reservation system is already developped, displaying the information to the user will only consist of a fetch operation from the database, and the corresponding UI design. | Medium | Low Risk- this is a low risk High value functional requirement | Hanine Tydrini | Sprint 2
#26 | As a customer, I want to have the option to add extra equipment | -Set up UI Set up UI to allow user to add extra equipment to his reservation for an extra cost #95 -Set up the logic to calculate and display the extra cost whenever a user selects extra equipment to add to the reservation. #96 | 3- It's imperative to be able to add extra equipment, but also to calculate the relating change of cost for the reservation dynamically. | High | Low Risk- this is a low risk High value functional requirement | Hanine Tydrini, | Sprint 2
#24 | As a customer, I want to see available fetch vehicles that correspond to the criteria I gave in my reservation form | -Fetch corresponding vehicles from database #93 - Display corresponding vehicles from database #94 | 4- Implementing good UI + fetching the corresponding data from the catalog of vehicles in the database, while applying the propefr filters correspondoing to the user's criteria | High | Low Risk- this is a low risk High value functional requirement | Hanine Tydrini, Yasmine Mouatif | Sprint 2
#23 | As a customer, I want to be able to fill a reservation form for my booking | -Create UI for user reservation form #91 -Handle user input validation and form submission #92 | 2 Implementing good UI is imperative, first impression of the user on our website. | High | Low Risk- this is a low risk High value functional requirement | yasmine Mouatif | Sprint 2
#20 | As a client, I want to be able to sort vehicles on the catalog page | -Create "Sort" button on Catalog page to sort vehicles based on different criteria #76 | 2- 3- Implement a good UI. Necessary feature to sort the available vehicles | High | Low Risk- this is a low risk High value functional requirement | Hanine Tydrini | Sprint 2
Sprint 3
Issue # | User Story Title/Task Title | Description/Associated Tasks | Difficulty Level (0,1,2,3,5,8) | Priority | Risk | Assign | Sprint
#167 | As a system administrator, I want to delete a branch location | As a system Administrator I want to be able to delete a branch as a system administrator in a case where we close down a location. | 3- This is an imperative part of the functional requirement we need to ensure functionality and consistency | High | Low Risk- this is a low risk High value functional requirement | sam, yasmine | Sprint 3
#166 | As a system administrator, I want to modify a branch location | In a case we have some changes in the branch location, such as hire new employees, or upsize, or downsize we need to be able to modify these details. | 3- This is imperative since it is necessary for the product we are renting on our platform, and alot of details are involved for a vehicle so we need adequate time to work on this, we would also need to integrate both front endand backend for this task. | High | Low Risk- This is a low risk High value functional requirement | sam, yasmine | Sprint 3
#165 | As a system administrator, I want to view available branch location | As a system Administrator I want to view the branches we have available in my system | 3- This is imperative since it is necessary feature for our users. ease of use. | High | Low Risk- This is a low risk High value functional requirement | sam, yasmine | Sprint 3
#165 | As a customer I want to be able to browse available branch locations | A customer needs to be able to browse all our branches to know which branch is closest to them. | 1- Provides good UX, and increases intuitiveness, and ease of access. | Low | Low Risk- This is a low risk High value functional requirement | ben, hanine | Sprint 3
#163 | As a customer I want to be able to find the nearest branch by providing a postal code or Airport | Once the user views the catalog, they can narrow down their vehicle selection by using their airport or postal code to see the branch locations nearest. | 3- Implement a good UI. Necessary feature to visualize the available vehicles | High | Low Risk- This is a low risk, Low value Not explicitly mentioned in our FRs | ben, hanine | Sprint 3
#155 | As a customer service representative, I shall be able to perform the payment settlement and conifrm the completion of the return process in the system | As a Customer service represntative, We need to be able to confirm payment with our customers, and ensure that vehicles are returned, incase we need to add additional charges for late return etc. | 3- Implement a good UI. Necessary feature to visualize the available vehicles | High | Low Risk- Low Risk, low value | uyi, ikram | Sprint 3
#154 | As a customer service representative, I shall be able to process a users final billing fee. | As a Customer service representative, we need to be able to provide our customer with their invoice, incase they need it for documentation processes. | 3- Being able to dynamically edit reservation details is imperative | Medium | High RIsk | uyi, ikram | Sprint 3
#153 | As a customer service representative, I shall be able to review rental agreements. |  | 3 - This is imperative since it is a necessary feature to manage users. Research needed to properly implement API endpoint. | High | Low Risk- this is a low risk High value functional requirement | uyi, ikram | Sprint 3
#189 | Handle Reservation creation, and confirmation | -The system should allow CSRs to submit a reservation request with all required details (customer information, reservation dates, vehicle selection). -Upon successful submission, the system should generate a unique reservation identifier. -Confirmation of the successful reservation creation should be displayed to the CSR, including reservation details and the unique identifier. | 5- Important tasks because our CSR's need this to be able to support our customer's request | High | High RIsk- This is a hugh risk, High Value functional requirement | yasmine | Sprint 3
#187 | As a Customer Service Representative, I shall be able to confirm the completion of the return process in the system |  | 3- This is imperative since, we need to be able to authenticate that our vehicles are returned, and update our database | Medium | "Low Risk- this is a low risk High value functional requirement" | uyi, ikram | Sprint 3
173 | As a CSR, I shall be able to take a customer to inspect a car upon his arrival at the selected pick-up location | Customers arrive at the designated pick-up location on the scheduled date and time to collect the rented car. They present their booking confirmation, valid driver's license, and the credit card used for reservation to a CSR. Additionally, customers can inspect the rented car with the CSR for any damages and report them to the rental agency if necessary. | 3- | Medium | Low Risk
#174 | As a CSR, I shall be able to make the Customer sign a rental agreement | CSR makes the Customers sign the rental agreement electronically or physically, agreeing to the terms and conditions of the rental. The system updates the status of the vehicle as rented and creates a link to the rental details, including duration, price, pick-up/drop-off location, and additional services, in the database. | 5- | High | Low Risk- this is a low risk High value functional requirement | yasmine | Sprint 3
#275 | As a CSR, I shall be able to take a deposit from the Customer before letting him drive away with his rental car | The system sends a request to the bank entity of the customer’s credit card used for making the reservation to take a deposit of 500 CAD. Users are free to drive away with the rented car and enjoy their trip if the deposit was successful. | 4- | High | Low Risk
Sprint 4
Issue # | User Story Title/Task Title | Description/Associated Tasks | Difficulty Level (0,1,2,3,5,8) | Priority | Risk | Assign | Sprint
#294 | As a customer, I want to have the option to list my car for rent. | This is our bonus additional feature, the point is to allow our customers to be able to submit a request to have their vehicles listed on our platform. | 3- This is an important task, however it is not part of our FRs | Medium | Low Risk- this is a low risk low value requirement | Benjamin Ho, Ikram Kamal | Sprint 4
#295 | As a System Administrator, I want to view the listing requests made by customers | The Goal of this user story is to be able to review requests of customers, and depending on the state of a vehicle, a system administrator can either accept or decline a customers request to have their vehicle | 2- This task should be fairly straight forward, as SA's are just tasked with rerviewing the requests catalog | Medium | Low Risk- this is a low risk low value requirement | Uyi Oronsaye, Ikram Kamal, Benjamin Ho | Sprint 4
#296 | As a System Administrator, I want to approve or decline a request made by a customer | The Goal of this user story is after reviewing customers listings, depending on the state of a vehicle, a system administrator can either accept or decline a customers request to have their vehicle | 2- This task should be fairly straight forward, as SA's are just tasked with accepting or declining customer's request. | Medium | Low Risk- this is a low risk low value requirement | Samuel Henderson, Ikram Kamal | Sprint 4
#318 | As a customer, I want to provide feedback and ratings for the rented vehicles and overall rental experience after checking out the car. | Customers should be able to leave feedback on a vehicle they have once reserved in the past for new customers to make decision based off past reviews. | 5- This task should take longer than usual, and it is a bit more difficult, as well it is also a functional requirement | High | High Risk - this is a high risk, high value functional requirement | Yasmine Mouatif, Hanine Tydrini | Sprint 4
#322 | As a customer, I want to see all the reviews linked to a specific car in the catalog | Customers should be able to view existing reviews left by other customers on each specific vehicle in our catalog so they can make well informed decisions on the vehicles they wish to rent. | 5- This task is a difficult task, so it is worth 8 story points, it is also a functional requirement | High | HIgh Risk - this is a high risk, high value functional requirement | Yasmine Mouatif, Hanine Tydrini | Sprint 4

## Burndown chart
BURNDOWN CHAT
Dates | Planned Tasks | Actual Tasks
Feb 12 | 10 | 10
Feb 13 | 8 | 8
Feb 14 | 8 | 8
Feb 15 | 8 | 7
Feb 16 | 8 | 7
Feb 17 | 7 | 7
Feb 18 | 7 | 7
Feb 19 | 7 | 7
Feb 20 | 7 | 7
Feb 21 | 6 | 7
Feb 22 | 6 | 6
Feb 23 | 6 | 7
Feb 24 | 6 | 6
Feb 25 | 5 | 6
Feb 26 | 5 | 6
Feb 27 | 5 | 4
Feb 28 | 5 | 4
Feb 29 | 5 | 6
March 1 | 5 | 3
March 2 | 4 | 3
March 3 | 4 | 3
March 4 | 4 | 3
March 5 | 4 | 3
March 6 | 4 | 3
March 7 | 3 | 2
March 8 | 3 | 2
March 9 | 2 | 2
March 10 | 1 | 2
March 11 | 1 | 1
March 12 | 10 | 9
March 13 | 10 | 8
March 14 | 8 | 8
March 15 | 8 | 6
March 16 | 8 | 9
March 17 | 7 | 6
March 18 | 7 | 6
March 19 | 7 | 6
March 20 | 7 | 6
March 21 | 6 | 4
March 22 | 3 | 4
March 23 | 3 | 3
March 24 | 3 | 3
March 25 | 1 | 1
BURNDOWN CHAT SPRINT 3
Dates | Planned Tasks | Actual Tasks
March 26 | 5
March 27 | 4
March 28 | 3
March 29 | 4
March 30 | 2
March 31 | 3
April 1 | 3
April 2 | 2
April 3 | 3
April 4 | 2
April 5 | 3
April 6 | 3
April 7 | 2
April 8 | 2
April 9 | 1
April 10 | 2

## TASK SPRINT 2
Issue # | Task Title | Description/Associated Tasks | Estimated Effort (0,1,2,3,5,8) | Dependency/Priority | Assign | Sprint
#98 | TASK 1.2.4.1 Send confirmation to user upon successful booking | Give the user options once he has selected confirm my booking | 2 | Low | Yasmine | 2
#97 | TASK 1.2.4.1 Set up reservation confirmation page UI | Set up the UI to display a reservation confirmation for the user after he has selected all options and details. | 3 | Low | Hanine | 2
#96 | TASK 1.2.3.1 Calculate the extra cost of extra equipment added to the reservation | Set up the logic to calculate and display the extra cost whenever a user selects extra equipment to add to the reservation. | 5 | Medium | Hanine | 2
#95 | TASK 1.2.3.1 Set up UI to allow user to add extra equipment to his reservation | Set up UI Set up UI to allow user to add extra equipment to his reservation for an extra cost | 3 | High | Hanine | 2
#94 | TASK 1.2.2.1 Display corresponding vehicles from database | Set up UI to display the vehicles corresponding to pickup and return criteria from the database previously fetched. | 5 | High | Hanine | 2
#93 | TASK 1.2.2.1 Fetch corresponding vehicles from database | Set up API call to fetch the vehicles corresponding to pickup and return criteria from the database. | 5 | High | Hanine | 2
#92 | TASK 1.2.1.2 Handle user input validation and form submission | Handle user input validation (valid date, valid location) and form submission | 3 | Medium | Yasmine | 2
#91 | TASK 1.2.1.1 Create UI for user reservation form | Create UI for a user reservation form that allows the user to input pickup date, return date and pickup and retuen location. | 3 | High | Yasmine | 2
#35 | TASK FE Create a UI for viewing, and modelling proces | Design and create UI to display a list of vehicles | 4 | High | Hanine | 2
#90 | TASK 1.3.3.2: Delete reservation from database | Implement a DELETE method to remove the reservation from the database | 3 | High | Sam | 2
#89 | TASK 1.3.3.1: Design UI for Delete Reservation Confirmation Popup | Design a UI popup for when a customer clicks on "Cancel Reservation" | 2 | High | Sam | 2
#88 | TASK 1.3.2.2: Update data in database upon modifications | Implement a PUT method to update the database after reservation changes are made | 3 | High | Sam | 2
#87 | TASK 1.3.2.1: Design UI for editable mode | Implement a transition to an editable UI after a user clicks on "Edit Reservation" | 4 | High | Ikram | 2
#85 | TASK 1.3.1.2: Fetch data from database to display in UI for "My reservations" page | Implement a fetch to display when the user is viewing a reservation | 3 | HIgh | Sam | 2
#84 | TASK 1.3.1.1: Design UI for a "My Reservations" page | Design a UI for customers to view their reservations | 3 | High | Sam | 2
#37 | TASK 3.2.1.1: Establish a connection between our server and MongoDB | Integrate MongoDB into our server by establishing a connection using Mongoose. | 2 | High | Ben | 2
#52 | TASK 3.2.1.2: Backend functionality to create new users | Implement a user creation API endpoint | 3 | High | Ben | 2
#54 | TASK 3.2.2.1: Backend functionality to read the details of users | Implement a user viewing API endpoint | 3 | High | Ben | 2
#79 | TASK 3.2.4.1: Backend functionality to delete a user | Implement a user deleting API endpoint | 3 | High | Ben | 2
#83 | TASK 3.2.3.1: Backend functionality to update users | Implement a user update API endpoint | 3 | High | Ben | 2
#29 | TASK 3.3.1.1: Design and Implement Frontend Reservation Creation Form for System Administartor | Design and implement a user-friendly form | 1 | high | Ikram | 2
#106 | TASK 3.3.1.2: Develop Backend API Endpoint for Creating Reservations by SA | Develop a backend API endpoint to handle the creation of reservations | 2 | medium | Sam | 2
#107 | TASK 3.3.1.4: Update Frontend to Display Confirmation Message by SA | provide users with immediate feedback upon successfully creating a reservation. | 2 | medium | Sam | 2
#109 | TASK 3.3.2.1: Design and Implement Frontend Reservations List Page for SA | Develop a user-friendly page in the frontend application | 5 | High | Ben | 2
#110 | TASK 3.3.2.2: Develop Backend API Endpoint for Fetching Reservations for | Create a backend API endpoint to retrieve a list of reservations from the database. | 5 | High | Sam | 2
#111 | TASK 3.3.2.3: Implement Filtering and Search Functionality in Frontend for SA | Enhance the frontend reservations list page by implementing filtering and search functionality. | 5 | Medium | Uyi | 2
#112 | TASK 3.3.3.1: Implement Frontend Option to Edit Reservations for SA | Implement a user friendly platfrom to edit reservations | 3 | Low | Ikram | 2
#113 | TASK 3.3.3.2: Backend API Endpoint for Updating Reservations by SA | Create a backend API endpoint specifically for updating existing reservations. | 5 | High | Sam | 2
#115 | TASK 3.3.3.4: Handle Form Submission by SA and Update Reservation Data in the Backend | Implement logic in the frontend application to handle form submission when system administrators modify reservations. | 3 | Medium | Sam | 2
#116 | TASK 3.3.4.1: Implement Frontend Option to Cancel Reservations for SA | Enhance the frontend interface for system administrators to include an option to cancel reservations. | 3 | Medium | Ikram | 2
#117 | TASK 3.3.4.2: Develop Backend API Endpoint for Canceling Reservations for | Create a dedicated backend API endpoint for system administrators to cancel reservations. | 5 | High | Sam | 2
#118 | TASK 3.3.4.3: Send Email Confirmation upon Reservation Cancellation by |  |  |  |  | 2
#68 | TASK 3.1.4.4 Test deletion functionality to make sure vehicles have been deleted and DBMS, and view updated. | Test Delete operation for system administrator for vehicle. | 1 | High | Uyi | 2
| TASK 3.1.4.3 Implement verification process to give SA cancel a deletion | verification process for deletion of a vehicle | 2 | High | Uyi | 2
#66 | TASK 3.1.4.2 BackEnd functionality to delete a specific vehicle | Delete Vehicle in the database side of the application | 2 | High | Uyi | 2
#65 | TASK 3.1.3.3 Test update functionality to ensure changes are modified and stored correctly | Ensure that updated data are implementd on both front and backEnd | 2 | High | Uyi | 2
#64 | TASK 3.1.3.2 Implement validation logic for updated vehicle details | Validate each entry of the updated vehicle | 2 | High | Uyi | 2
#63 | TASK 3.1.3.1 BackEnd Functionality to update vehicle details | Search function for unique ID of each Vehicle. | 2 | High | Uyi | 2
#62 | TASK 3.1.2.2 Test read functionality, and make sure searched vehicles are displayed appropriately. | Test Read Operation for SA on each vehicle | 2 | High | Uyi | 2
#61 | TASK 3.1.2.1 Backend functionality to retrieve vehicle data associated with the unique ID | showcasing the details of the vehicle associated with a searched ID | 2 | High | Uyi | 2
#60 | TASK 3.1.4.1. Create UI search features to find vehicles via Unique ID | search function for unique ID of each Vehicle. | 2 | High | Uyi | 2
#103 | TASK 3.2.3.2: Design UI for removing / modifying a user | As a developer, I want to display two buttons on the bottom of the user's information page to modify and remove a user | 1 | high | Ikram | 2
#101 | TASK 3.2.1.3: Design UI to create a new user | As a developer, I want to display a button "Add user" on the user list page | 2 | high | Ikram | 2
#82 | TASK 1.1.3.2: Design UI for Vehicule page | As a developer, I want to design the user interface for the vehicle pages displayed when a vehicle is selected to display informations | 3 | high | Hanine | 2
#81 | TASK 1.1.3.1: Redirect user to a new page when vehiocule is selected | As a developer, I want to display a new page whenever a user clicks on a vehicle on the Catalog page. | 2 | medium | Hanine | 2
#79 | TASK 1.1.2.1: Create "Sort" button on Catalog page to sort vehicules based on different criteraia | As a developer, I want to add a sort button on the Catalog page to sort the displayed vehicles based on type, price, brand or transmission. | 2 | low | Hanine | 2
#75 | TASK 1.1.1.1: Design UI for catalog page | As a developer, I want to design and create the user interface for the catalog page | 3 | high | Ikram | 2
#73 | TASK 1.1.1: Create a "Catalog link on the navigation | As a developer, I want to add a Catalog option on the navbar to lead me to the catalog page. | 1 | high | Ikram | 2

## TASK SPRINT 3
Issue # | Task Title | Description | Estimated Effort (0,1,2,3,5,8) | Dependency/Priority | Assign | Sprint
196 | Task 2.1.3.2 Display Check-in successful UI upon deposit confirmed #196 | Design UI page upon deposit successfully processed. Show all reservation details and check-in details. Give option to print of send check-in confirmation by email. | 3 | high |  | 3
195 | Task 2.1.3.2 Process Deposit Confirmation in Backend #195 | Implement functionality to process confirmation of the deposit from the bank entity. | 1 | low |  | 3
194 | Task 2.1.3.1 Develop Deposit Request Feature #194 | Develop UI for the system to take a deposit from the customer. Develop functionality for the system to send a deposit request to the bank entity. | 5 | high | hanine | 3
193 | Task 2.1.2.3 Update Rental Details in Database | Update the rental details in the database to store including duration, price, pick-up/drop-off location, and additional services. | 2 | low |  | 3
192 | Task 2.1.2.2 Update Vehicle Status upon Customer Pick-up | Implement a feature to update the status of the vehicle as currently rented in the system, if not already unavailable. | 2 | medium |  | 3
191 | Task 2.1.2.1 Develop Rental Agreement Signing Feature | Create a rental agreement as UI. Develop functionality for users to sign the rental agreement electronically or physically. | 3 | high | hanine | 3
189 | Task 2.1.1.2: Implement Car Inspection for customers | Implement a feature for users to inspect the rented car for damages. Customer can report any damages to the company if there are any. | 2 | medium | hanine | 3
188 | Task 2.1.1.1: Design and Implement Check-In Process UI | Develop a check-in process for users to present required documents and collect the rented car. Customers need to present: booking confirmation, valid driver's license, the credit card that they used to make the reservation. | 2
197 | Task 1.4.1.1: Display Branch Locations List |  | 1 | medium |  | 3
198 | Task 1.4.1.2: Implement Map View Option |  | 2 | low |  | 3
| TASK 2.2.1.1: Desing UI for rental agreements #233 | UI for rental agreements | 1 | medium | ikram | 3
233 | TASK 2.2.1.2: Update rental agreements status in backend #234 | Create PATCH method to update the rental agreements status from "unreviewed" to "reviewed" | 2 | medium | sam | 3
234 | TASK 2.2.2.1: Design UI for Payment Settlement Page |  | 1 | medium |  | 3
261 | TASK 2.2.2.2: Update reservation status indicating that billing payment was sent | Make patch request after submission of button to update reservation status from "not sent" to "sent" | 2 | medium | ben | 3
262 | TASK 2.2.2.3: Send email with payment details and settlement | Design bill, Send billing payment to email | 2 | low | uyi | 3
263 | Task 1.4.1.3: Enable List View | display a List view option on the Branch page | 2 | low | yasmine | 3
199 | Task 1.4.1.4: Enable Map View | display a Map view option on the Branch page | 2 | high | yasmine | 3
201 | TASK 1.4.2.1: Implement search bar | implement a search bar component for the branch location feature. | 3 | high | yasmine | 3
209 | TASK 1.4.2.2: Validate the user input | implement validation logic for user input in the search bar of the branch location feature | 2 | low | yasmine | 3
210 | TASK 1.4.2.3: Retrieve Branch Data | implement functionality to retrieve branch data from the database in response to user input in the search bar of the branch location feature. | 2 | low | ben | 3
211 | TASK 1.4.2.4: Create UI to display Nearest Branch | create a user interface to display the nearest branch after a search | 1 | medium | ikram | 3
212 | TASK 1.4.3.1: Create Branch Page on System Administrator Side | create a new page for available branch locations on System Administrator page | 2 | low | uyi | 3
213 | TASK 1.4.3.2: Backend functionality to read branch data | implement backend functionality to read branch data from database. | 2 | medium | uyi | 3
214 | TASK 1.4.3.3: Create UI to display branch listing | design and implement the user interface to display branch listing on the Administrator side | 2 | high | yasmine | 3
215 | TASK 1.4.4.1: Design UI for Edit branch option #216 | implement an edit option on each branch | 2 | medium | yasmine | 3
216 | TASK 1.4.4.2: Backend functionality to modify branch | implement a function to modify branch info | 2 | medium | sam | 3
217 | TASK 1.4.5.1: Design UI for Delete branch option | implement a Delete option on each branch on the frontend | 1 | medium | yasmine | 3
218 | TASK 1.4.5.2: Backend functionality to delete branch | I want to implement a function to remove branch in the database | 2 | medium | sam | 3
230 | TASK 2.2.3.1: Design UI for confirmation of a return #230 | UI for a confirmation of a return | 1 | high | ikram | 3
231 | TASK 2.2.3.2: Send (return) confirmation to users email #231 | send a confirmation to the user's email after the return | 2 | medium | ikram, yasmine | 3
232 | TASK 2.2.3.3: Update Data in database to confirm vehicle was successfully returned | update the return status in the reservatio… | 2 | high | ben | 3

## TASK SPRINT 4
Issue # | Task Title | Description | Estimated Effort (0,1,2,3,5,8) | Dependency/Priority | Assign | Sprint
#298 | Task 4.1.1: Design and implement page for listing car rental requests on the customer interface | As a Developer, I want to implement a page for customers to view their requests or/and make a request to list their car for rent. | 3 | high | Ikram Kamal | 4
#299 | Task 4.1.2: Create request form | As a Developer I want to create a form for customers who want to put their car for rent. The form should be similaire to the form used to add new vehicle by system administrator. | 1 | low | Ikram Kamal | 4
#300 | Task 4.1.3: Display confirmation message after submission | As a system Administrator, I want to display a confirmation message after submitting the request form to confirm that the form has been successfully submitted and an agent is evaluating the request. | 5 | high | Hanine Tydrini | 4
#301 | Task 4.1.4: Backend functionality to save the request in the database | As a system Administrator, I want to create a database to save the requests made by customers. When a customer submit a request, the request should be saved to the database and its status should be set to "In Progress". | 2 | low | Benjamin Ho | 4
#302 | Task 4.2.1: backend functionality to update status on the customer side accordingly | As a system Administrator,, I want to update the status of the request on the customer side after a decision is made by system administrator. Once the status is updated on the database, it should be displayed to the customer. | 2 | medium | Uyi Oronsaye | 4
#303 | Task 4.3.1: Implement a dedicated page for system administrators to view car listing requests from customers. | As a system Administrator,, I want to implement a page for system administrator dedicated to view requests made by customers. | 3 | high | Hanine Tydrini | 4
#304 | Task 4.3.2: Display requests made by customers and saved in the database | As a system Administrator, I want to display the request made by customers on the request management page. The requests are saved on the database and displayed on the admin side. | 2 | medium | Ikram Kamal | 4
#305 | Task 4.3.3: Display all the listing details when selecting a request | As a system Administrator, I want to display all details of a request when a system administrator select a specific request. An option "Show more" should be displayed to the system administrator to display all information requested by customer. | 2 |  | Uyi Oronsaye | 4
#306 | Task 4.4.1: Implement Approve/Decline button on the requests listing | As a system Administrator, I want to implement an Approve and Decline button on the requests management page and on each pending request made by customers. | 1 | medium | Yasmine Mouatif | 4
#307 | Task 4.4.2: Send email to alert customer of the request decision | As a system Administrator, I want to send an email to notify the customer of the request decision. If system administrator select "Approve", customer receives an email saying that his request has been approved and his car has been added to the catalog. Otherwise, he receives an email with the reason why his request has been declined. | 2 | low | Samuel Henderson | 4
#308 | Task 4.4.3: Update status of a request by system administrator | Task 4.4.3: Update status of a request by system administrator | 1 | medium | Benjamin Ho | 4
#309 | Task 4.4.4: Add vehicle to the catalog if request is approved | Create PATCH method to update the rental agreements status from "unreviewed" to "reviewed" | 2 | medium | Samuel Henderson | 4
#319 | TASK 1.5.1.1: Implement UI changes to add a "Review" button within the "My Reservations" tab | Update the user interface to include a clickable button labeled "Review" within the "My Reservations" tab. This button should be visually distinct and easily identifiable to prompt users to leave a review for their reservations. | 2 | medium | Yasmine Mouatif | 4
#320 | TASK 1.5.1.2: Create a form component for submitting ratings and reviews | Develop a form component that allows users to input their ratings (1-5 stars) and write a review for their reservation. Ensure proper validation of form. | 2 | low | Yasmine Mouatif | 4
#321 | TASK 1.5.1.3: Implement backend logic to associate ratings and reviews with specific reservations | Add review instance in backend that stores the review linked to the specific reservation and car. | 2 | low | Uyi Oronsaye | 4
#323 | TASK 1.5.2.1: Implement UI changes to display a section for reviews within the car details page | Update the user interface of the car details page to include a dedicated section for displaying reviews associated with the selected car. | 2 | high | Hanine Tydrini | 4
#324 | TASK 1.5.2.2: Create a component to fetch and display reviews associated with a specific car | Develop a reusable component responsible for fetching and displaying reviews linked to a specific car. | 3 | high | Benjamin Ho | 4