## Samuel Henderson
Name: | Samuel Henderson
| Date | Task Type | Description | Start Time | End Time | Duration
Sprint 1
| 2024-02-04 | Documentation | Security Measurements & Conclusion | - | - | 2h
| 2024-02-06 | Documentation | Creation of User Story and Tasks | - | - | 1h
| 2025-02-08 | Development | Reservation schema creation and model | - | - | 1h30
| 2024-02-08 | Development | Reservation routes and controllers | - | - | 2h
| 2025-02-09 | Documentation | Update User Stories | - | - | 1h
| 2025-02-10 | Documentation | Burndown Chart | - | - | 25mins
Sprint 2
| 2024-03-20 | Development | Integrated CREATE with Booking Form | - | - | 1h
| 2024-03-02 | Development | Created Reservation Cards | 19:00 | 21:00 | 2h
| 2024-03-05 | Development | Implemented CRUD operatios onto reservation management page | 19:00 | 24:00 | 5h
| 2024-03-07 | Documentation | Creation of User Stories for Checkout Process | 19:30 | 20:30 | 1h
| 2024-03-08 | Development | Reservation Logic | 20:30 | 2:30 | 6h
| 2024-03-09 | Documentation | Added pricing Logic | 19:30 | 20:20 | 1h
| 2024-03-09 | Documentation | Creation of Acceptance Tests issues | 20:30 | 21:00 | 30min
| 2024-03-10 | Development | Unit Tests | 19:00 | 22:00 | 3h
| 2024-03-11 | Documentation | Recording of Acceprance Tests | 19:00 | 19:30 | 30min
Sprint 3
| 2024-03-15 | Documentation | UML creation for sequence diagram of process 2 | 14:00 | 15:00 | 1h
| 2024-03-18 | Development | Creation of branches in database | 19:00 | 21:00 | 2h
| 2024-03-20 | Development | Integration of branches with frontend | 19:00 | 20:00 | 1h
| 2024-03-20 | Development | Integration of reservations backend with checkin | 20:00 | 21:00 | 1h
| 2024-03-21 | Development | Integration of reservation backend with checkout | 19:00 | 21:30 | 1h30
| 2024-03-22 | Development | Email confirmation on booking creation, modification, or deletion | 19:00 | 24:00 | 5h
| 2024-03-23 | Development | Email confirmation on deposit take | 24:00 | 2:00 | 2h
| 2024-03-23 | Development | Email confirmation on deposit returned, and vehicle returned | 19:00 | 21:00 | 3h
| 2024-03-24 | Development | Credit Card Creation and logic | 19:00 | 23:30 | 4h30
Sprint 4
| 2024-04-01 | Development | Integration of backend for additional features | 20:00 | 2:00 | 6h
| 2024-04-08 | Development | Integration of backend for status update and email logic | 18:00 | 21:00 | 3h
| 2024-04-09 | Development | Integration of backend for status update and email logic | 12:45 | 2:45 | 2h
| 2024-04-09 | Refactoring | Code review for Appendix B | 17:00 | 20:00
| 2024-04-10 | Development | Email confirmations to customer owned vehicles | 17:00 | 18:00 | 1h

## Benjamin Ho
Name: | Benjamin Ho
| Date | Task Type | Description | Start Time | End Time | Duration
Sprint 1
| 2024-02-03 | Documentation | Project Overview and Approach | - | - | 2 hours
| 2024-02-04 | Documentation | User story and tasks creation | - | - | 1 hour
| 2024-02-06 | Development | Backend server setup | - | - | 2 hours
| 2024-02-08 | Development | Users API | - | - | 2 hours
| 2024-02-09 | Documentation | Git Rule WIki | - | - | 1 hour
| 2024-02-10 | Documentation | Project Timeline | - | - | 30 minutes
Sprint 2
| 2024-02-20 | Development | Implemented READ,UPDATE,DELETE API endpoints for users | - | - | 1 hour
| 2024-03-03 | Development | Integrated CREATE and DELETE users backend with frontend | - | - | 2 hours
| 2024-03-04 | Development | Error handling for the AddClientForm | - | - | 2 hours
| 2024-03-06 | Development | Integrated DELETE user backend with frontend | - | - | 1 hour
| 2024-03-06 | Documentation | Creation of Acceptance Tests issues for CRUD user stories | - | - | 1 hour
| 2024-03-07 | Development | Creation unit tests for user model and controllers | - | - | 4 hours
| 2024-03-09 | Documentation | Created issues for signup, login, logout features | - | - | 2 hours
| 2024-03-09 | Development | Implemented signup, login, logout backend | - | - | 6 hours
| 2024-03-10 | Development | Implemented role-based access control | - | - | 2 hours
| 2024-03-11 | Development | Added missing route guards | - | - | 1 hour
Sprint 3
| 2024-03-14 | Documentation | Acitivity Diagram for Process 2 (Check-in) | 12:00 | 12:30 | 30 mins
| 2024-03-22 | Research | Research on Google Maps API | 9:00 | 11:00 | 2 hours
| 2024-03-22 | Development | Implemented map and autocomplete for "Find a branch" feature | 14:00 | 18:00 | 4 hours
| 2024-03-24 | Development | Added error handling and redirection for location search from Home Page | 15:30 | 19:30 | 4 hours
| 2024-03-25 | Development | Fixed login/signup bugs and improved user experience | 15:00 | 17:00 | 2 hours
| 2024-03-25 | Documentation | Sequence Diagram for Process 2 (Check-in) | 18:30 | 19:00 | 30 mins
| 2024-03-25 | Documentation | Create and record ATs for "Find a branch" feature | 20:00 | 20:30 | 30 mins
Sprint 4
| 2024-04-08 | Development | Modified user model to cater to new feature | 20:00 | 22:00 | 2 hours
| 2024-04-09 | Development | Implemented emails to cater to new feature | 18:30 | 22:30 | 4.5 hours
| 2024-04-10 | Development | Fixed SendGrid API key bug | 8:30 | 9:30 | 1 hour
| 2024-04-10 | Refactoring | Code Review | 6:30 | 10:30 | 4 hours

## Ikram Kamal
Name: | Ikram Kamal
| Date | Task Type | Description | Start Time | End Time | Duration
Sprint 1
| 2024-02-04 | Documentation | Breakdown of sprint 1 | - | - | 30min
|  | Documentation | Project Approach document | 10:00 | 11:30 | 1h30min
| 2024-02-05 | Documentation | Create of User Stories | - | - | 30min
| 2024-02-07 | Development | Design and create UI for Navbar + System admin pages | - | - | 2h30min
| 2024-02-08 | Documentation | Create Time tracking template and Burndown chart | - | - | 30min
|  | Documentation | Create User Stories
|  | Documentation | Project Approach document | 18:00 | 19:30 | 1h30
Sprint 2
| 2024-02-23 | Research | CI Github | 11:30 | 3:00 | 4h30
| 2024-02-23 | Research | CI Github | 20:00 | 21:30 | 1h30
| 2024-02-25 | Development | Client database UI | 20:00 | 22:00 | 2h
| 2024-02-26 | Development | Client Form | 20:00 | 21:30 | 1h30
| 2024-02-28 | Development | Add client form UI, Reservation search UI | 20:00 | 22:00 | 2h
| 2024-03-05 | Development | Add Modify feature for client | 8:00 | 10:00 | 2h
| 2024-03-06 | Documentatiom | Create US for sprint 3 | 13:00 | 14:30 | 1h30
| 2024-03-07 | Documentatiom | Create TASKS for sprint 3 and AT for sprint 2 | 15:00 | 17:00 | 2h
| 2024-03-08 | Development | Create UI for login page | 20:00 | 22:00 | 2h
| 2024-03-09 | Development | Create different pages for different types of users | 18:00 | 20:00 | 2h
| 2024-03-09 | Testing | Creation of Unit tests | 20:30 | 22:00 | 1h30
| 2024-03-10 | Testing | Record videos for acceptance tests | - | - | 45min
Sprint 3
| 2024-03-12 | Research | Research for map api and design branch page | 14:00 | 16:00 | 2h
| 2024-03-14 | Development | Implement Branch page | 15:00 | 16:00 | 1h
| 2024-03-17 | Development | Create map and listing option for branches, retrieve branches data from backend | 19:00 | 21:30 | 2h30
| 2024-03-18 | Development | Finalizing UI for branch page / Create search bar on homepage | 15:00 | 17:30 | 2h30
| 2024-03-19 | Testing | Testing UI for branch page | 14:00 | 15:00 | 1h
| 2024-03-21 | Documentation | Activity diagram for process 1 | 14:00 | 15:00 | 1h
| 2024-03-23 | Development | Implementing logic to calculate distance of an input address and selected branch | 14:00 | 18:00 | 4h
| 2024-03-24 | Documentation | Create user stories and tasks for sprint 4 | 21:00 | 23:00 | 2h
Sprint 4
| 2024-03-26 | Documentation | Modification of the US for sprint 4 | 14:00 | 16:00 | 2h
| 2024-03-27 | Development | UI implementation for new feature | 17:00 | 21:30 | 4h30
| 2024-04-02 | Development | Form request implementation and modification on the UI | 14:00 | 17:00 | 3h
| 2024-04-08 | Development | Modifications on the request form and implementations of view option for customers | 16:00 | 20:00 | 4h
| 2024-04-10 | Development | Digital inspection request form | 17:00 | 19:30 | 2h30
| 2024-04-10 | Documentation | Acceptance tests

## Uyi Oronsaye
Name: | Uyi Oronsaye
| Date | Task Type | Description | Start Time | End Time | Duration
Sprint 1
| 2024-02-01 | Research | Searching for valuable Third party APIs | - | - | 0.5 hours
| 2024-02-02 | Documentation | Integration and interoperability description | - | - | 2 hours
| 2024-02-10 | Documentation | Creaton of User Stories | - | - | 1 hour
| 2024-02-10 | Documentation | Breakdown User stories into tasks, and Subtask | - | - | 2 hours
| 2024-02-11 | Documentation | Planning for the next sprint 2. (Burndown sheet, and word doc) | - | - | 2 hours
| 2024-02-07 | Development | Vehicle database schema | - | - | 0.5 hours
Sprint 2
| 2024-02-14 | Development | Defined Model, and schema, and routes for vehicle |  |  | 1 hour
| 2024-02-15 | Research | CI/CD implementation | - | - | 1 hour
| 2024-02-13 | Development | Setup the CI/CD, and cleaned up all the errors, to ensure the test is setup. | - | - | 2 hours
| 2024-02-14 | Development | Implement Create functionality, and help with back,frontend integration | - | - | 3 hours
| 2024-02-15 | Development | Implement Read functionality, and help with back,frontend integration | - | - | 3 hours
| 2024-02-19 | Development | Implement Update functionality, and help with back,frontend integration | - | - | 3 hours
| 2024-02-21 | Development | Implement Delete functionality, and help with back,frontend integration | - | - | 3 hours
| 2024-02-22 | Testing | Creating issues for Acceptance Test | - | - | 1 hours
| 2024-02-23 | Documentation | BurnDown chart for Sprint 3 | - | - | 3 hours
| 2024-02-27 | Testing | Creating Acceptabce test videos for issues | - | - | 2 hours
| 2024-03-10 | Documentation | Added tags to task, difficulty, and task tyope | - | - | 0.5 hour
| 2024-03-10 | Development | Fixed backend components, and model for Vehicles | - | - | 1 hour
| 2024-03-11 | Dvelopment | Fixed Filter logic for displaying cars bases on type, and category. | - | - | 3 hours
Sprint 3
| 2024-03-12 | Research | Determining which API (easy invoice, stripe) that will be used to process user payments, and and create necessarty invoice for customers | 16:00 | 17:40 | 1.67 hours
| 2024-03-14 | Development | Work on creating backend functionality to capture billing information information such as billing Address, totalcost etc.(controllers, model, routes). | 9:30 | 12:15 | 3 hours
| 2024-03-15 | Research | How to handle using the twilio API to handle emails | 10:10 | 11:15 | 1 hour
| 2024-03-16 | Development | Create Middleware to include our stripePayments API, generated an API key for managing connection to API endpoints, and eventually created route to handle payment processing | 11:00 | 12:00 | 1 hour
| 2024-03-18 | Development | Created message prompt for sending receipt to customer, after payment confirmation | 12:00 | 13:00 | 1 hour
| 2024-03-20 | Documentation | Created the UML diagram for sequences for process 3 (Checkout), | 22:30 | 0:20 | 1 hour
| 2024-03-22 | Development | Create Unit Tests, and finalzing the CI/CD correction to working directory | 10:00 | 13:15 | 3.5 hours
| 2024-03-22 | Development | Write working Unit Tests for Vehicles Model, Controllers | 9:40 | 11:30 | 2 hours
| 2024-03-24 | Documentation | Worked on creating burndown sheet for all the user stories for sprint 4 | 12:10 | 13:00 | 1 hour
| 2024-03-24 | Documentation | Worked on creating task planning sheet for all the tasks in sprint 4, and assiging task on gitHub | 13:15 | 15:00 | 2 hours
| 2024-03-25 | Research | Search for CI/CD working directory setup | 14:15 | 16:00 | 2 hours
Sprint 4
| 2024-03-27 | Development | Modified backend database to cater to our new added feature, added status , custoner_ID, and description for vehicle applications | 10:00 | 13:15 | 3.5 hours
| 2024-03-30 | Development | Worked on implementing filter logic for separating customer application vehicles, from our rentaroo created vehicles in our catalog | 10:00 | 16:15 | 6 hours
| 2024-03-02 | Development | Handled the sprting, and filtering of vehicles visible in the Customer Request side on the System Administrator page | 14:00 | 16:00 | 2 hours
| 2024-04-10 | Development | Modified vehicle class model, and controller to accept new images for digital inspection | 9:30 | 10:20 | 1 hour
| 2024-04-10 | Documentation | Worked on Acceptance Test for US 4.1, as a user i can apply for my vehicle to be featured on the website.

## Yasmine Mouatif
Name: | Yasmine Mouatif
| Date | Task Type | Description | Start Time | End Time | Duration
Sprint 1
| 2024-02-05 | Documentation | Created a README for the project | 16:20 | 17:45 | 1:45
| 2024-02-06 | Documentation | Creation of user stories | 14:00 | 15:15 | 1:15
| 2024-02-08 | Documentation | Added information to the README | 15:10 | 16:15 | 1:05
| 2024-02-08 | Development | Created/shared figma project and started design of logo & Booking form | - | - | 2:00
| 2024-02-09 | Development | Booking Form Creation | 13:20 | 15:30 | 2:10
| -- | Documentation | Overall Planning meetings and formatting meeting minutes | - | - | 2:30
Sprint 2
| 2024-02-16 | Development | Create and updated Booking form | 16:00 | 17:40 | 1:40
| 2024-02-20 | Development | Added css to booking form | 14:15 | 15:05 | 0:50
| 2024-02-27 | Development | Connected the catalog to the booking Form | 10:10 | 11:15 | 1:15
| 2024-03-05 | Development | Modify Reservation Feature | 11:00 | 12:00 | 1:00
| 2024-03-07 | Development | Developped View Reservation Page for Client | 9:30 | 12:15 | 2:45
| 2024-03-08 | Development | Terms And Conditions Page Added | 22:30 | 0:20 | 1:50
| 2024-03-10 | Development | Finished View Reservation Page for Client | 10:00 | 13:15 | 3:15
| 2024-03-11 | Development | Updated UI to remove conflicts | 9:40 | 11:30 | 1:50
| 2024-03-11 | Testing | Recorded Acceptance Test Videos | 12:10 | 13:00 | 0:50
| 2024-03-11 | Testing | Unit Test Programming | 13:15 | 16:00 | 2:45
Sprint 3
| 2024-03-15 | Documentation | UML Creation for sequence diagram of process 3 | 16:30 | 17:45 | 1:15
| 2024-03-20 | Development | Creation of CheckOut Page | 10:15 | 14:00 | 3:45
| 2024-03-21 | Development | Style CheckOut Page | 12:05 | 13:45 | 1:40
| 2024-03-22 | Development | Created and Linked Checkout to Car Return Form | 14:12 | 16:20 | 2:08
| 2024-03-22 | Development | Created and Linked Checkout to Payment Settlement Form | 17:00 | 18:15 | 1:15
| 2024-03-23 | Development | Updated Payment Settlement Page | 10:00 | 12:35 | 2:35
| 2024-03-23 | Development | Created Payment Confirmation Page | 12:35 | 14:00 | 1:25
| 2024-03-24 | Development | Updated backend status when returning the car | 13:00 | 14:10 | 1:10
Sprint 4
| 2024-03-29 | Development | Started Additional UI for Additonal Features Page | 19:00 | 21:00 | 2:00
| 2024-03-30 | Development | Finished UI and functions for Additional Features | 12:15 | 15:00 | 2:45
| 2024-04-03 | Documentation | Looked into sonarQube installation and beenfits | 17:30 | 18:30 | 1:00
| 2024-04-10 | Development | SonarQube Set Up | 10:05 | 13:20 | 3:15
| 2024-04-10 | Development | SonarQube Development for static analysis | 14:30 | 18:00 | 3:30
| 2024-04-10 | Devleopment | Acceptance Tests | 20:15 | 21:00 | 0:45
| 2024-04-10 | Documentation | Wiki for static analysis | 21:00 | 22:15 | 1:15

## Hanine Tydrini
Name: | Hanine Tydrini
| Date | Task Type | Description | Start Time | End Time | Duration
Sprint 1
| 2024-02-04 | Documentation | Project approach and Technology (3.1) and research | - | - | 3:00
| 2024-02-04 | Development | React project creation and setup | 20:10 | 21:00 | 0:50
| 2024-02-06 | Documentation | Create User Stories and tasks | - | - | 1:30
| 2024-02-07 | Documentation | Design UI for Catalog page on Figma | 17:45 | 18:45 | 1:00
| 2024-02-04 | Development | Create UI for Catalog page | 20:00 | 21:00 | 1:00
| 2024-02-07 | Development | Catalog page logic implementation + mock database to view vehicles | 19:00 | 23:00 | 4:00
| 2024-02-08 | Development | Catalog page sorting feature implementation + additional information popup | 23:00 | 1:00 | -0.91667
| 2024-02-10 | Documentation | Team members: roles and background | 18:30 | 19:20 | 0:50
Sprint 2
| 2024-02-19 | Development | Catalog page sorting feature + updates + styling | 21:30 | 23 | 530:30
| 2024-02-26 | Development | Frontend Backend intergration, Read on vehicles | 15 | 18 | 3
| 2024-02-29 | Development | System Administrator vehicle catalog; logic and integration with backend | 20:30 | 23:50 | 3:20
| 2024-03-04 | Development | UI for Administrator CRUD operations | 20:00 | 23:30 | 3:30
| 2024-04-06 | Development | Modify and Create operation on vehicles | 12:00 | 14:15 | 2:15
| 2024-04-06 | Development | Home page UI | 14:15 | 14:45 | 0:30
| 2024-03-06 | Development | Catalog Additional vehicle information; changed implementation + book now | 14:45 | 16:30 | 1:45
| 2024-03-08 | Development | Start a Reservation as Customer | 16:45 | 18:30 | 1:45
| 2024-03-10 | Development | Start Reservation Filters logic implementation + UI | 11:00 | 13:50 | 2:50
| 2024-03-10 | Development | Start a resevation styling + form implementation | 19:45 | 21:15 | 1:30
| 2024-03-08 | Development | User Stories creation sprint 3 |  |  | 1:30
| 2024-03-10 | Research/Development | Unit tests | 20:00 | 23:45 | 3:45
| 2024-03-11 | Development | Unit tests |  |  | 3:00
| 2024-03-11 | Documentation | Sprint 3 project planning on Wiki pages Github |  |  | 0:30
| 2024-03-11 | Documentation | Acceptance tests | 20:00 | 22:00 | 2:00
Sprint 3
| 2024-03-20 | Development | CSR Search for customer reservation for check-in | 12:00 | 14:30 | 2:30
| 2024-03-20 | Development | Vehicle inspection check-in UI | 14:30 | 15:30 | 1:00
| 2024-03-21 | Development | Inspection backend + rental agreement UI | 14:00 | 17:00 | 3:00
| 2024-03-21 | Development | rental agreement fetching vehicle & user information | 17:00 | 18:00 | 1:00
| 2024-03-21 | Development | update rental agreement + solve bugs | 21:00 | 0:05 | -0.87153
| 2024-03-22 | Development | Deposit UI fot check-in | 0:05 | 1:15 | 1:10
| 2024-03-24 | Development | Deposit handeling confirmation page | 14:30 | 17:15 | 2:45
| 2024-03-25 | Documentation | Acceptance tests | 13:00 | 14:00 | 1:00
| 2024-03-26 | Documentation | Sprint 4 planning | 14:30 | 15:00 | 0:30
| 2024-03-27 | Documentation | Sequence diagram | 20:00 | 20:40 | 0:40
0
Sprint 4
| 2024-04-05 | Documentation | Repo Reorganising Attempts 1 | 14:00 | 16:30 | 2:30
| 2024-04-07 | Development | Managing Custumer Requests to rent out their vehicles (UI + logic) | 17:00 | 22:45 | 5:45
| 2024-04-09 | Development | Styling on SA side | 13:00 | 13:55 | 0:55
| 2024-04-10 | Development | Digital Inspection added to SA Request Management Page | 20:45 | 22:30 | 1:45
| 2024-04-09 | Documentation | Repo Reorganising Attempts 2 | 20:00 | 21:20 | 1:20
| 2024-04-10 | Development | Fixing bugs + issues | 21:30 | 22:30 | 1:00
| 2024-04-10 | Documentation | Acceptance Tests | 22:30 | 0:00 | -0.9375