## Feuille 1
Name: | Hanine Tydrini | [5 empty] | Name: | Yasmine Mouatif
| Date | Task Type | Description | Start Time | End Time | Duration |  | Date | Task Type | Description | Start Time | End Time | Duration
Sprint 1 | [6 empty] | Sprint 1
| 2024-02-04 | Documentation | Project approach and Technology (3.1) and research | - | - | 3:00 |  | 2024-02-05 | Documentation | Created a README for the project | 16:20 | 17:45 | 1:45
| 2024-02-04 | Development | React project creation and setup | 20:10 | 21:00 | 0:50 |  | 2024-02-06 | Documentation | Creation of user stories | 14:00 | 15:15 | 1:15
| 2024-02-06 | Documentation | Create User Stories and tasks | - | - | 1:30 |  | 2024-02-08 | Documentation | Added information to the README | 15:10 | 16:15 | 1:05
| 2024-02-07 | Documentation | Design UI for Catalog page on Figma | 17:45 | 18:45 | 1:00 |  | 2024-02-08 | Development | Created/shared figma project and started design of logo & Booking form | - | - | 2:00
| 2024-02-04 | Development | Create UI for Catalog page | 20:00 | 21:00 | 1:00 |  | 2024-02-09 | Development | Booking Form Creation | 13:20 | 15:30 | 2:10
| 2024-02-07 | Development | Catalog page logic implementation + mock database to view vehicles | 19:00 | 23:00 | 4:00 |  | -- | Documentation | Overall Planning meetings and formatting meeting minutes | - | - | 2:30
| 2024-02-08 | Development | Catalog page sorting feature implementation + additional information popup | 23:00 | 1:00 | -0.91667
| 2024-02-10 | Documentation | Team members: roles and background | 18:30 | 19:20 | 0:50
Sprint 2 | [6 empty] | Sprint 2
Sprint 3 | [6 empty] | Sprint 3
Sprint 4 | [6 empty] | Sprint 4
Name: | Ikram Kamal | [5 empty] | Name: | Uyi Oronsaye
| Date | Task Type | Description | Start Time | End Time | Duration |  | Date | Task Type | Description | Start Time | End Time | Duration
Sprint 1 | [6 empty] | Sprint 1
| 2024-02-04 | Documentation | Breakdown of sprint 1 | - | - | 30min |  | 2024-02-01 | Research | Searching for valuable Third party APIs | - | - | 0.5 hours
|  | Documentation | Project Approach document | 10:00 | 11:30 | 1h30min |  | 2024-02-02 | Documentation | Integration and interoperability description | - | - | 2 hours
| 2024-02-05 | Documentation | Create of User Stories | - | - | 30min |  | 2024-02-10 | Documentation | Creaton of User Stories | - | - | 1 hour
| 2024-02-07 | Development | Design and create UI for Navbar + System admin pages | - | - | 2h30min |  | 2024-02-10 | Documentation | Breakdown User stories into tasks, and Subtask | - | - | 2 hours
| 2024-02-08 | Documentation | Create Time tracking template and Burndown chart | - | - | 30min |  | 2024-02-11 | Documentation | Planning for the next sprint 2. (Burndown sheet, and word doc) | - | - | 2 hours
|  | Documentation | Create User Stories |  |  |  |  | 2024-02-07 | Development | Vehicle database schema | - | - | 0.5 hours
|  | Documentation | Project Approach document | 18:00 | 19:30 | 1h30
Sprint 2 | [6 empty] | Sprint 2
Sprint 3 | [6 empty] | Sprint 3
Sprint 4 | [6 empty] | Sprint 4
Name: | Samuel Henderson | [5 empty] | Name: | Benjamin Ho
| Date | Task Type | Description | Start Time | End Time | Duration |  | Date | Task Type | Description | Start Time | End Time | Duration
Sprint 1 | [6 empty] | Sprint 1
| 2024-02-04 | Documentation | Security Measurements & Conclusion | - | - | 2h |  | 2024-02-03 | Documentation | Project Overview and Approach | - | - | 2 hours
| 2024-02-06 | Documentation | Creation of User Story and Tasks | - | - | 1h |  | 2024-02-04 | Documentation | User story and tasks creation | - | - | 1 hour
| 2025-02-08 | Development | Reservation schema creation and model | - | - | 1h30 |  | 2024-02-06 | Development | Backend server setup | - | - | 2 hours
| 2024-02-08 | Development | Reservation routes and controllers | - | - | 2h |  | 2024-02-08 | Development | Users API | - | - | 2 hours
| 2025-02-09 | Documentation | Update User Stories | - | - | 1h |  | 2024-02-09 | Documentation | Git Rule WIki | - | - | 1 hour
| 2025-02-10 | Documentation | Burndown Chart | - | - | 25mins |  | 2024-02-10 | Documentation | Project Timeline | - | - | 30 minutes
Sprint 2 | [6 empty] | Sprint 2
Sprint 3 | [6 empty] | Sprint 3
Sprint 4 | [6 empty] | Sprint 4